## Action Items
VayuSync review: prioritized action items
Source: review of repo commit 65efe8a (Oct 10, 2026). Yellow cells (Owner, Status) are for you to edit.
Total items | 5
Open | 5
In progress | 0
Done | 0
Rank | Area | Finding | Evidence | Recommended action | Verified how | Owner | Status
1 | Demo behaviour | Flagship /simulate demo returns no alerts: all three simulator presets send smoke toward 120-124 deg, but Delhi is at about 150-153 deg from Ludhiana. With a 15 deg half-angle the cone misses every institution, even the 12 h cone. | Ran the three presets through the fixed geo_utils: 0 of 8 institutions in the cone for 6 h and 12 h (see 'Cone Coverage' sheet). Your own diagnostics also saw an empty alert array in 234 ms. | Make a Haryana hotspot (Karnal/Panipat, about 100-120 km from Delhi) the headline demo with a NNW wind (~350 deg). Keep Punjab as the extended-range story with a NNW wind (~330 deg). Make the evaluator check the 12 h cone too (it only reads cone_geojson_6h). Check what a judge actually sees after clicking Simulate. | Reproduced locally with repo code |  | Open
2 | Bedrock / AI claim | Bedrock is not live right now: AccessDenied ('account being verified'), so hosted advice is rule-based. README row 77 still says 'Live Bedrock Invocation'. | AccessDeniedException reported from CloudWatch (your report); advisory_source field exists in evaluator code; README line 77 unchanged. | Reword the README until a real /simulate record shows advisory_source = 'bedrock'. When verification completes, confirm model access is enabled and Claude 3 Haiku is still available in ap-south-1. | Code + README read; AccessDenied taken from your report |  | Open
3 | Frontend honesty | The UI can show mock numbers next to live ones: api.ts fills missing dashboard fields from MOCK_DASHBOARD using '??' (lead time, latency, cost, alert counts). | grep of frontend/src/utils/api.ts only; not tested in a browser. | Show a dash or a visible 'demo data' badge for any field that falls back to mock values. | grep only (not browser-tested) |  | Open
4 | CI / testing | A missing 'import math' in the evaluator (introduced in cbef7bd) shipped in Lambda Version 1 and was hidden by a generic exception handler. The 34 tests did not catch it. | Reported in your diagnostics; import now present at line 34 of evaluator_engine/handler.py. | Add a smoke test that imports every Lambda handler with boto3 stubbed, so a missing import fails CI. | Code read |  | Open
5 | Validation | No real back-test has been run yet. The self-test uses synthetic data and is not validation. | backend/scripts/backtest.py self-test passes; sandbox cannot reach FIRMS, Open-Meteo or CPCB. | Run backtest.py on your machine for one real event, commit backtest_results.csv, and share the raw JSON output for a sanity check. | Self-test run; real run not possible here |  | Open

## Cone Coverage
Do the simulator presets reach Delhi? (Ludhiana hotspot)
Inputs (blue = hardcoded; edit to test other targets)
Cone half-angle (deg) | 15 | geo_utils.py DEFAULT_CONE_HALF_ANGLE_DEG
Bearing Ludhiana to Anand Vihar (deg) | 150.2 | Computed with the haversine bearing formula; Ludhiana (30.9, 75.85), station (28.6476, 77.3158, approximate). AIIMS Delhi gives 152.8
Distance Ludhiana to Anand Vihar (km) | 287.7 | Computed with geo_utils.haversine_distance
Preset results
Preset | Smoke heads toward (deg) | 6 h reach (km) | 12 h reach (km) | Institutions in cone (of 8) | Miss angle (deg) | Preset wind blows from (deg) | Wind would need to blow from (deg) | Within cone angle? | Reaches Delhi at 6 h? | Reaches Delhi at 12 h? | Covers target at 12 h?
worst_case | 120.3 | 176.5 | 353.1 | 0 | 29.9 | 300.3 | 330.2 | No | No | Yes | No
moderate | 123.7 | 134.4 | 268.9 | 0 | 26.5 | 303.7 | 330.2 | No | No | No | No
light | 121 | 67.3 | 134.6 | 0 | 29.2 | 301 | 330.2 | No | No | No | No
Notes
Reach and bearing values were produced by running the simulator presets (u, v from simulate_trigger/handler.py) through the fixed calculate_trajectory_cone at commit 65efe8a.
Assumption: fire power set to the middle of each preset's range (worst_case 1,250 MW; moderate 950 MW; light 600 MW), which affects reach slightly through the buoyancy factor.
'Institutions in cone' is the count from the script run against the 8 mock institutions in mock_data.py; it is not recalculated here.
Miss angle is the smaller angle between the preset's bearing and the bearing to Delhi; a target is inside the cone only if this is at most the half-angle AND the cone reaches its distance.
Demo wind direction in meteorological terms is where the wind blows FROM; smoke heads toward the opposite direction (add 180).

## Verified Changes
What I checked in commit 65efe8a
Item | Result | Detail
import math in evaluator_engine/handler.py | Confirmed | Present at line 34.
advisory_source field (bedrock / rule_fallback) | Confirmed | Set in the evaluator; bedrock_model is 'rule_fallback' unless Bedrock actually answered.
Unit tests (test_pipeline.py) | Confirmed | 34 tests run, 2 skipped, 0 failures in my sandbox.
backtest.py self-test | Confirmed | Passes, including the NW-wind bearing check (135 deg). Synthetic data, not validation.
geo_utils sign fix across all six copies | Confirmed | All use atan2(u_wind, v_wind) as of cbef7bd.
README link to backtest.py | Confirmed | Now a relative path.
README row 77 'Live Bedrock Invocation' | Needs change | Still says live; Bedrock was AccessDenied in your diagnostics.
API Gateway throttling (5 req/s, burst 10) | Not verified | I cannot see your AWS account settings.
Lambda redeployments and live /simulate calls | Not verified | I cannot reach your AWS account; figures come from your report.
Latency figures (1,127-2,400 ms; 234 ms) | Not verified | Need a CloudWatch Logs Insights query with N and p95.
Confirmed | 6
Needs change | 1
Not verified | 3